## Tracking Sheet
Plan
Lead Generatiom
Google Ads
Goal 30 Leads a Month | October | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total | Move thru Escort , RS4, Panigale, MotoGP
Reviewed existing Web Pages (score 78% target 88% Forecast 2% conversion | October: x; Nov: 10th Nov |  | Measure Effectiveness, Review, Learn, Tweak
Poor web Pages read like a brochure design V1 Landing Pages Padel Hostel & Locker - Purity test (forecast 2% conversion) | October: x; Nov: October |  | Should be review only after Q1
https://vpod.com/crowdstor/lp-hostel-hotel-luggage-smart-locker-rental/ | October: x; Nov: 21st Nov |  | Lower cost per Lead £35,000 / 4
https://vpod.com/crowdstor/lp-padel-equipment-rental-solution/ | October: x; Nov: 21st Nov |  | ie £7500
No 1 Existing Web Pages Speed Fix (for seo https://www.communicationsedge.co.uk/vpod-speed-case-study | [16 empty] | Q1 will ascertain what we can reduce to
No 2 Upgrade These to New Specs 4% conversion) | Nov: ? Rory / Josh
No 3 Upgrade these to 6% conversion | Dec: SH / PT |  | 28200 | SH
See Upgrade Plan here | Dec: SH / Lindi (Measurement ); Jan: SH / Lindi (Nurture) |  | 16800 | purity
Objectives | Nov: Escort; Dec: RS4; Jan: Panigale; Feb: MotoGP |  | 36000 | Ads cost | 3000 | Ad Spend Average
1. deliver 30 leads a month | Nov: Template V1; Dec: Template V2; Jan: Value Trade Assets; Feb: Full Nurture plan |  | 81000 | Total cost
2. Test Diagnostic framework data - does it give the insights we need to learn & support Purity |  |  | Leads | 10 | 20 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 15 | 15 | 15 | 255 | 255 | Leads | 8925000 | Pipeline
3. Refine Landing Pages from v1 learns and purity feedback | [16 empty] | 317.6471 | Cost per Lead
SH Time | 8 days | 8 days | 4 Days | 4 Days | 4 Days | 4 Days | 2 Days | 2 Days | 2 Days | 1 Day | 1 Day | 1 Day | 1 Day | 1 Day | 1 Day |  | 63.75 | Deals
Observations | 500 | 500 | 500 | 600 | 600 | 600 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 |  | 35000 | Deal size
Current cost per Lead 8 months labour & Ad Campaign £31,451 (4 Leads) £7,862.75 per lead | 4000 | 4000 | 4000 | 2400 | 2400 | 2400 | 1500 | 1500 | 1500 | 750 | 750 | 750 | 750 | 750 | 750 | 28200 | 2231250 | Deals
Average Deal £35,000 Margin 50%
SEO
Reviewed previous SEO 2024 - volumes collapsed from 667 per month organic (70% of traffic) to 2 visitors a month
Why? Poor site Migration, Poor Indexing Discipline (none in 10 months), poor page speed = high bounce rates
Impact? Conversion damaged , costs increased as having to use PPC Google Ads
Goal - Reduce Cost per Lead by minimum 30-40%
Goal - Reduce Risk of competitor attack from someone with a large wallet (PE / VC funded)
Methodology
Reviewed Current webpages that are not designed for SEO conversion - 47 keywords of 843 ranked average 67th place
Fixed Page speed which delivers 6X traffic increase to 12 visitors instantly - https://www.communicationsedge.co.uk/vpod-speed-case-study
Indexed all Pages
Target | October | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec |  | Create all the assets to rank for 187 keywords
Rank for Padel,Hostel & Hotel, Parcel, Asset, Workplace, Leisure & Event Lockers - 4,500 search volume exact match, 9,000 broad match) | Dec: Start Publishing; Jan: Start Publishing; June: 10% of Traffic 450 visitors; Dec: 20% of traffic 900 visitors |  | Nail the personas, pain points & briefs,
Effort Required - Full Time Marketing Intern 1 Year £17.5-27.5k age 17-19 & Fractional CMO (£40k) (briefs, quality , coaching, reviewing) | Jan: Smart Locker |  | Manage the execution & content score lift
Upside will take 6 months to reach 450 visitors a month 12 months to hit 900 (visitors a month) | Jan: Workplace |  | Flat out till June to get momentum
Downside have to invest whilst still spending on PPC , Albeit month 7-12 should be able to taper PPC by 25% then 50% | Jan: Parcel |  | Relies 60% on intern for £2200 a month / £110 a day
After 12 months switch intern to 50% SEO Maintenance 50% Partner Marketing | Jan: Paddle |  | Requires daily coaching and reviews
SEO PLAN - See SEO section in | Jan: Hostel & Hotel
Gettting Traffic is pointless if it doesn't convert therefore the pages have to a) Rank b) Convert | Jan: Asset
Conversion needs a minimum of for 4 sectors 22 Personas & their 66 Pain Points handle with content (currently 100% absent from the website) | [16 empty] | Metrics 2026 |  | 2027 | Both Years
If we add Event, Leisure & Hostel & Hotel - then we are adding 12+ personas and 30+ Pain Points | [16 empty] | 27500 | SEO FTE | 13500 | 41000
For Each Pain Point a) needs a Pillar, Cluster & Blog strategy to rank, b) to convert the traffic = 100 pages MINIMUM & 100 Topical Blogs | May: Leads; June: 10; July: 10; Aug: 10; Sept: 20; Oct: 30; Nov: 30; Dec: 15 | 125 | 56400 | SH | 9000 | 65400
200 High Quality Pages = 1 FTE a Year - Hence the intern | Nov: Hire Intern; Dec: Hire Intern |  | 83900 | Total SEO | 22500 | 106400
SH Time | 4 Days | 4 Days | 4 days | 8 Days | 8 Days | 8 Days | 8 Days | 8 Days | 8 Days | 4 Days | 4 Days | 4 Days | 4 Days | 4 Days | 4 Days |  | 125 | Leads | 360 | 485
Note most assets in SEO will be transferable to Partners | 500 | 500 | 500 | 600 | 600 | 600 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 |  | 671.2 | CPL year 1 | 62.5 | 219.3814
Assumes no nurture plan for pipeline to increase conversion from 25% (I would council that is worth building in H2) | 2000 | 2000 | 2000 | 4800 | 4800 | 4800 | 6000 | 6000 | 6000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 56400 | 35000 | Deal size
[17 empty] | 4375000 | Revenue Pipeline
[18 empty] | 2025 | 2026
[18 empty] | Lead cost | Lead cost | Lead cost
[18 empty] | 7500 | 671.2 | 62.5
[19 empty] | 8.949% | 0.8333%
Partner
Re-Use SEO Personas & Pain Points Assets with SPS - Delivery & Front of House | October | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Interview SPS Marketing Director & GTM Leader with PT | Nov: Interview SPS |  | Tweak all the assets for partners
Design Partner Portal Assets for SPS | Dec: SH; Jan: SH / Josh |  | Move from Parcel & Guest to Padel , Asset, Smart, Luggage, Event & Leisure
Deliver Ricoh Partner Portal "Triggers" for Business Development & PT - in HubSpot with Lindi | Jan: SH / Lindi |  | IE SPS focus then others
Create Nurture Campaigns for all salesteam variants - Pareto Top 20% first IE target SPS top 60 sales folk | [16 empty] | Lindi instals all triggers
SH makes sure we hit commercial Goals
PT determines when the priorities are added
SH Time | 0 | 0 | 4 Days | 4 Days | 3 Days | 3 Days | 2 Days | 2 Days | 2 days | 1 Day | 1 Day | 1 Day | 1 Day | 1 Day | 1 Day
|  |  | 2000 | 2400 | 1800 | 1800 | 1500 | 1500 | 1500 | 750 | 750 | 750 | 750 | 750 | 750
| 12 | 12 | 12 | 16 | 15 | 15 | 12 | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6
Day Rate | 500 | 500 | 500 | 600 | 600 | 600 | 600 | 600 | 600 | 750 | 750 | 750 | 750 | 750 | 750
| 6000 | 6000 | 6000 | 9600 | 9000 | 9000 | 7200 | 7200 | 7200 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
Assumptions
Partner Portal is in the same state as PPC & SEO
No other large projects loom - Nurture path pipeline, Expansion path existing customers | October: Fix; Nov: Fix; Dec: Learn PPC; Jan: Upgrade PPC; Feb: Refine PPC
|  |  | Partner Portal Review & Upgrade | Start SEO